## OVERVIEW
TMS (FT LAUD) 11/11
229 | 182005955
TMS (FT LAUD) 10/11
228 | 182005723
TMS (FT LAUD) 9/11
227 | 182005680
TMS (FT LAUD) 8/11
226 | 182005662
TMS (FT LAUD) 7/11
225 | 182005640
TMS (OAKLAND PARK) 6/11
224 | 182005584
TMS (FT LAUD) 5/11
223 | 182005510
TMS (WILTON MANORS) 4/11
222 | 182005465
TMS (WILTON MANORS) 3/11
221 | 182005439
TMS (FT LAUD) 2/11
220 | 182005356
TMS (FT LAUD) 1/11
219 | 182005288
TMS IT836-19-1DB (MIAMI)
200 | 135004792
TMS IT836-19-1TL (MIAMI)
199 | 135004792
TMS IT836-18-1TL (MIAMI)
197 | 135004681
TMS IT836-18-1DB (MIAMI)
196 | 135004681
TMS IT836-17-2TL (MIAMI)
195 | 135004627
TMS IT836-17-1TL (MIAMI)
194 | 135004589
TMS IT836-17-7DB (MIAMI)
193 | 135004563
TMS IT836-17-6DB (MIAMI)
192 | 135004681
TMS IT836-17-4DB (MIAMI)
191 | 135004529
TMS IT836-17-3DB (MIAMI)
190 | 135004501
TMS IT836-17-2DB (MIAMI)
189 | 135004471
TMS IT836-16-5DB (MIAMI)
188 | 135004412
TMS IT836-16-3DB (MIAMI)
187 | 135004393
TMS IT836-16-2DB (MIAMI)
186 | 135003752
TMS IT836-16-1DB (MIAMI)
185 | 135004341
TMS IT836-14-4TL (MIAMI)
184 | 135003904
TMS IT836-14-8DB (MIAMI)
180 | 135003752
TMS IT836-14-4DB (MIAMI)
179 | 135003673
TMS IT836-12-2DB (MIAMI)
178 | 135003602
TMS IT836-17-8DB (85') MIAMI
172 | 134003697
TMS IT836-17-1DB (337') MIAMI
171 | 134003694
TMS IT836-16-6DB (232') MIAMI
170 | 134003694
TMS IT836-16-7DB (131') MIAMI
169 | 134003689
TMS 144 Dolphin Stadium
165 | 130000003
133000013
133000014
TMS IT836-12 (120') MIAMI
163 | 128006952
TMS IT836-14-1DB (125') MIAMI
152 | 114006428
TMS IT836-13-1DB (161') MIAMI
149 | 114006315
TMS CO 139-72 NE 13TH ST. BORES DAMAGED (MIAMI)
146 | 106002397
106002410
TMS PROJECT ID 251688-1-52-01 (MIAMI)
145 | 105006641
105006644
105006647
105006652
106002314

## 229
TMS (FT LAUD) 11/11
182005955
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | MCI | 1: Marked
| Current | PRECISION CONTRACTING SERVICES INC | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site

## 228
TMS (FT LAUD) 10/11
182005723
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 5: No Conflict - utility is outside of the requested work site
| Current | PRECISION CONTRACTING SERVICES INC | 1: Marked
| Current | CITY OF OAKLAND PARK | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | BROWARD COUNTY WATER AND WASTEWATER SERVICES | 5: No Conflict - utility is outside of the requested work site

## 227
TMS (FT LAUD) 9/11
182005680
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | PRECISION CONTRACTING SERVICES INC | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked

## 226
TMS (FT LAUD) 8/11
182005662
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | PRECISION CONTRACTING SERVICES INC | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site

## 225
TMS (FT LAUD) 7/11
182005640
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | PRECISION CONTRACTING SERVICES INC | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site

## 224
TMS (OAKLAND PARK) 6/11
182005584
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | PRECISION CONTRACTING SERVICES INC | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | CITY OF OAKLAND PARK | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking | 2020/07/07 15:22 I SPOKE WITH CESAR AND HE WILL BE SENDING ME AERIALS

## 223
TMS (FT LAUD) 5/11
182005510
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | CITY OF FT LAUDERDALE | 5: No Conflict - utility is outside of the requested work site
| Current | PRECISION CONTRACTING SERVICES INC | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site

## 222
TMS (WILTON MANORS) 4/11
182005465
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | FDOT/ELAND ENGINEERING | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 3U: Unmarked - Not service provider for this location
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | PRECISION CONTRACTING SERVICES INC | 1: Marked
| Current | CITY OF WILTON MANORS | 3U: Unmarked - Not service provider for this location
| Current | CITY OF OAKLAND PARK | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked

## 221
TMS (WILTON MANORS) 3/11
182005439
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | FDOT/ELAND ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance
| Current | PRECISION CONTRACTING SERVICES INC | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | CITY OF WILTON MANORS | 3U: Unmarked - Not service provider for this location
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CITY OF OAKLAND PARK | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked

## 220
TMS (FT LAUD) 2/11
182005356
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | PRECISION CONTRACTING SERVICES INC | 4: Clear No Facilities
| Current | CITY OF FT LAUDERDALE | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked

## 219
TMS (FT LAUD) 1/11
182005288
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 3U: Unmarked - Not service provider for this location
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | PRECISION CONTRACTING SERVICES INC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked

## 200
TMS IT836-19-1DB (MIAMI)
135004792
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM. DON'T DIG OR START WORK UNTIL CLARIFY THE AREA IN QUESTION WITH ANY CONTACT NAME
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | MASTEC INC | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site | 2020/05/22 13:39 REFER TO TKT # 15004681 FOR PICTURES. MARKED FPL &amp; ATT/D FIBER OPTIC. ATT/D FIBER OPTIC &amp; 50 PAIR COPPER CABLE GO TO D.O.T HUB,NO ACCESS TO HUB AREA
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 5: No Conflict - utility is outside of the requested work site

## 199
TMS IT836-19-1TL (MIAMI)
135004792
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM. DON'T DIG OR START WORK UNTIL CLARIFY THE AREA IN QUESTION WITH ANY CONTACT NAME
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | MASTEC INC | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site | 2020/05/22 13:39 REFER TO TKT # 15004681 FOR PICTURES. MARKED FPL &amp; ATT/D FIBER OPTIC. ATT/D FIBER OPTIC &amp; 50 PAIR COPPER CABLE GO TO D.O.T HUB,NO ACCESS TO HUB AREA
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 5: No Conflict - utility is outside of the requested work site

## 197
TMS IT836-18-1TL (MIAMI)
135004681
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM. DON'T DIG OR START WORK UNTIL CLARIFY THE AREA IN QUESTION WITH ANY CONTACT NAME
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | AT T | 1: Marked | NULL
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked

## 196
TMS IT836-18-1DB (MIAMI)
135004681
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM. DON'T DIG OR START WORK UNTIL CLARIFY THE AREA IN QUESTION WITH ANY CONTACT NAME
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | AT T | 1: Marked | NULL
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked

## 195
TMS IT836-17-2TL (MIAMI)
135004627
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 4: Clear No Facilities | FPL IS CLEAR, PRIVATE POWER NEEDS TO BE LOCATED.
| Current | SPRINT | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site | 2020/05/18 12:58 CONFLICT
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | AT T | 1: Marked | NULL
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 194
TMS IT836-17-1TL (MIAMI)
135004589
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | FPL MARKED AREA, PRIVATE POWER NEEDS TO BE LOCATED.
| Current | SPRINT | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/18 12:32 FPL AREA MAJOR CONFLICT FOR ATT/D FACILITIES
| Current | MCI | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 193
TMS IT836-17-7DB (MIAMI)
135004563
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 4: Clear No Facilities | FPL IS CLEAR, PRIVATE POWER NEEDS TO BE LOCATED
| Current | SPRINT | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/18 11:02 FPL AREA
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND MARKED BY TMS.
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 192
TMS IT836-17-6DB (MIAMI)
135004681
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM. DON'T DIG OR START WORK UNTIL CLARIFY THE AREA IN QUESTION WITH ANY CONTACT NAME
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | AT T | 1: Marked | NULL
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked

## 191
TMS IT836-17-4DB (MIAMI)
135004529
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 4: Clear No Facilities | FPL IS CLEAR, PRIVATE POWER NEEDS TO BE LOCATED.
| Current | SPRINT | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 13:34 FPL AREA
| Current | MCI | 4: Clear No Facilities
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 190
TMS IT836-17-3DB (MIAMI)
135004501
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 4: Clear No Facilities | FPL IS CLEAR, PRIVATE POWER NEEDS TO BE LOCATED
| Current | SPRINT | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/18 14:14 MAJOR CONFLICT FOR ATT/D FACILITIES. REFER TO TKT # 133000012 FOR PICTURES,MARKED FOR SAME CONTRACTOR 05/18. FPL AREA
| Current | MASTEC INC | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 3R: Unmarked - The excavator has performed the excavation prior to the locaters arrival

## 189
TMS IT836-17-2DB (MIAMI)
135004471
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 4: Clear No Facilities | FPL IS CLEAR, PRIVATE POWER NEEDS TO BE LOCATED
| Current | MCI | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/18 14:13 MAJOR CONFLICT FOR ATT/D FACILITIES. REFER TO TKT # 133000012 FOR PICTURES,MARKED FOR SAME CONTRACTOR 05/18. FPL AREA
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 3R: Unmarked - The excavator has performed the excavation prior to the locaters arrival

## 188
TMS IT836-16-5DB (MIAMI)
135004412
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 13:24 CONFLICT REFER TO TKT # 135004393 FOR PICTURES.
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.

## 187
TMS IT836-16-3DB (MIAMI)
135004393
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 13:23 CONFLICT REFER TO TKT # 135004393 FOR PICTURES.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND AREA MARKED BY TMS.

## 186
TMS IT836-16-2DB (MIAMI)
135003752
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | MIAMI- DADE COUNTY IT DEPT | 5: No Conflict - utility is outside of the requested work site | PLEASE MAKE NOTE. BURIED CABLE NEARBY. DO NOT DIG ON NORTH WITHOUT LETTING US KNOW. SEE ATTACHED
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 07:56 CONFLICT
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND ARE MARKED COMPLETED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 185
TMS IT836-16-1DB (MIAMI)
135004341
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | FPL MARKED THEIR PORTION OF THIS TICKET, CENTERLINE HEADING NORTH ON 14ST AND NW 10AVE. USIC DOES OTHER PORTION OF THIS TICKET
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 13:31 CONFLICT REFER TO TKT # 135004393 FOR PICTURES.
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND ARE MARKED BY TMS.

## 184
TMS IT836-14-4TL (MIAMI)
135003904
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/18 11:43 CONFLICT,MET PITO ON SITE. EFER TO TKT # 135003904 FOR PICTURES. NEEDS ONLY 140 FEET GOING EAST FROM NW 12 AVE
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 180
TMS IT836-14-8DB (MIAMI)
135003752
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | MIAMI- DADE COUNTY IT DEPT | 5: No Conflict - utility is outside of the requested work site | PLEASE MAKE NOTE. BURIED CABLE NEARBY. DO NOT DIG ON NORTH WITHOUT LETTING US KNOW. SEE ATTACHED
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/16 07:56 CONFLICT
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND ARE MARKED COMPLETED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 179
TMS IT836-14-4DB (MIAMI)
135003673
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 5: No Conflict - utility is outside of the requested work site | NO CONFLICT. PLEASE MAKE NOTE: BURIED CABLE NEARBY, ALONG NORTH SIDE OF RAMP. IF YOUR DIG PLANS CHANGE TO GO NORTH, PLEASE LET US KNOW IMMEDIATELY
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND ARE MARKED COMPLETED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site

## 178
TMS IT836-12-2DB (MIAMI)
135003602
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 4: Clear No Facilities
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE AND ARE MARKED COMPLETED BY TMS.
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 172
TMS IT836-17-8DB (85') MIAMI
134003697
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/14 13:52 REFER TOTKT # 1330000011 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR FPL AREA
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | SPRINT | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 3P: Unmarked - Member does not have accurate information to perform the requested locate - please contact the utility for further details per 556.105 (7)(a), F.S. | TICKET EXPIRED.

## 171
TMS IT836-17-1DB (337') MIAMI
134003694
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/14 13:38 REFER TOTKT # 1330000010 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR 2020/05/14 13:51 REFER TOTKT # 1330000010 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 3P: Unmarked - Member does not have accurate information to perform the requested locate - please contact the utility for further details per 556.105 (7)(a), F.S. | TICKET EXPIRED.

## 170
TMS IT836-16-6DB (232') MIAMI
134003694
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/14 13:38 REFER TOTKT # 1330000010 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR 2020/05/14 13:51 REFER TOTKT # 1330000010 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 3P: Unmarked - Member does not have accurate information to perform the requested locate - please contact the utility for further details per 556.105 (7)(a), F.S. | TICKET EXPIRED.

## 169
TMS IT836-16-7DB (131') MIAMI
134003689
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 3U: Unmarked - Not service provider for this location
| Current | CENTURYLINK | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/14 13:37 REFER TOTKT # 133000009 FOR PICTURES MARKED 05/14 FOR SAME CONTRACTOR
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 3P: Unmarked - Member does not have accurate information to perform the requested locate - please contact the utility for further details per 556.105 (7)(a), F.S. | TICKET EXPIRED.

## 165
TMS 144 Dolphin Stadium
130000003
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA CITY GAS | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | A T &amp; T/ DISTRIBUTION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked
| Current | NMB WATER/JACOBS | 1: Marked
133000013
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA CITY GAS | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | NMB WATER/JACOBS | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 3A: Unmarked - Locate technician could not gain access to property, call member to schedule access.
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site | 2020/05/14 16:05 THIS EMAIL IS TO INFORM YOU THAT THE TICKET REFERENCE BELOW AS BEEN PLACE ON DELAY AND WON'T BE COMPLETED UNTIL FRIDAY (5/15/20), IF YOU HAVE QUESTION PLEASE FEEL FREE TO CONTACT ME AT 786-417-9430 REF TICKET# FROM: IRTHNET AT: 05/12/20 07:27 AM SEQ NO: 14 FPLDAD 00791 CALL SUNSHINE 05/12/20 03:27:07ET 133000013-000 GRID TICKET : 133000013 REV:000 TAKEN: 05/12/20 03:25ET STATE: FL CNTY: DADE GEOPLACE: MIAMI GARDENS CALLERPLACE: MIAMI GARDENS SUBDIVISION: ADDRESS : STREET : FLORIDA'S TPKE CROSS 1 : NW 199TH ST WITHIN 1/4 MILE: Y LOCAT: NORTH OF PARKING LOT 13 TO THE EAST OF DOLPHIN STADIUM, THERE IS AN EXIT RAMP FROM TURNPIKE. NORTH OF TOLL BOOTH THERE IS A SMALL BUILDING. STARTING AT THE SE CORNER OF THE BUILDING, LOCATE EAST ALONG NORTHERN SIDE OF ROAD FOR APPROX 200FT. FOLLOW WHITE LINES. MARK ALL EASEMENTS AND RIGHT OF WAYS. : REMARKS : *** LOOKUP BY MANUAL *** : GRIDS : 2557B8013A WORK DATE: 05/14/20 TIME: 23:59ET HRS NOTC: 068 CATEGORY: 3 DURATION
133000014
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/05/12 14:48 NOT MARK YET LINK TO TICKET NUMBER 133000013
| Current | NMB WATER/JACOBS | 1: Marked

## 163
TMS IT836-12 (120') MIAMI
128006952
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--DADE | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 1: Marked | LOCATE COMPLETE. AREA MARKED BY TMS.

## 152
TMS IT836-14-1DB (125') MIAMI
114006428
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | MIAMI DADE EXPRESSWAY AUTHORITY -MDX | 4: Clear No Facilities | NO CONFLICT BASED ON THE INFORMATION.
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/27 14:56 CONFLICT
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked

## 149
TMS IT836-13-1DB (161') MIAMI
114006315
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 8: Ongoing Job - locate technician and excavator have established an agreement on scheduled marking
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/29 12:39 ON GOING,NEED UTILITY ASSISTANCE FOR FPL FEEDER. REFER TO TKT # 114006315 FOR PICTURES. LEFT MSG TO MIKE ( 954-599-1947 ),DELAYED REQUESTED DUE NEED TO MARKED FPL FEEDER( NO SIGNAL ) 2020/05/04 16:09 TALKED TO MIKE 05/05 2:55 PM,HE AGREED TO CALL ME PRIOR TO BORE OR DIG WATING FOR FPL ( EDGAR ) TO LOCATE FEEDER ( DIR/BORE ) NOT ENERGIZED AS 05/05,NO SIGNAL. 2020/05/11 15:06 MET PITO &amp; GERARDO ON SITE I RECOMMEND THEM TO OPEN TRENCH INTERSECTION OF NW 14 AVE &amp; NW NORTH RIVER DR VERY CONGESTED AREA FOR FACILITES STILL WAITING FOR " FPL ( EDGAR &amp; ANGEL ) TO LOCATE FEEDER # 455955,NO SIGNAL DUE SWITCH CUT OFF ARE HANGING REFER TO TKT # 126004271 FOR MORE PICTURES. 2020/05/19 11:38 CONFLICT

## 146
TMS CO 139-72 NE 13TH ST. BORES DAMAGED (MIAMI)
106002397
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED. THIS LOCATE WAS NOT WHITE LINED.
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | AT T | 1: Marked | NULL
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
106002410
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:59 CONFLICT FPL AREA REFER TO TKT # 105006652 FOR PICTURES MARKED 04/15 FOR SAME CONTRACTOR 04/15
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MCI | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities

## 145
TMS PROJECT ID 251688-1-52-01 (MIAMI)
105006641
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS CALL STEVE AT (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM. ON SITE MEET REQUIRED TO REVIEW FPL TRANSMISSION AS-BUILT 24HR PRIOR TO EXCAVATION OR DIRECT BORING CONTACT STEVE (305) 797-8459 TO SCHEDULE A MEET, OPERATION HR. TO CALL M-F 6:00 AM-2:30PM.
| Current | AT T | 1: Marked | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/16 15:48 CONFLICT REFER TO TKT # 105004817 FOR PICTURES. MARKED FOR " NEW ERA ELECTRIC INC " 04/16
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CENTURYLINK | 1: Marked
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
105006644
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | AT T | 3T: Extraordinary circumstances per 556.105(8)(a), F.S. exist, call utility owner / operator provider for this location. | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 3N: Unmarked - Locate description is insufficient - white lining is required per 556.114(3), FS Please contact the utility when the white lining is completed.
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
105006647
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:24 CONFLICT FPL AREA
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CENTURYLINK | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
105006652
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3M: Unmarked - Marking instructions are unclear, call the utility to clarify the marking instructions. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | FLORIDA GAS TRANSMISSION | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/15 15:45 CONFLICT,TWO RUN FOR ATT/D FACILITIES FPL AREA.
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MIAMI-DADE WATER &amp; SEWER | 5: No Conflict - utility is outside of the requested work site
| Current | CENTURYLINK | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
106002314
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MIAMI- DADE COUNTY IT DEPT | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS CALL STEVE AT (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM.
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | AT T | 1: Marked | NULL
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date. | THE FDOT'S FACILITY WILL BE LOCATED BY A CONTRACTOR (TMS)TRAFFIC MANAGEMENT SOLUTION. THIS CONTRACTOR WILL BE LOCATE IN THOSE AREAS IN (I95 &amp; FROM NW 8 ST TO NW 29 ST) AND WHEN I-395 BEGIN UNTIL 1200 FT FROM THE BISCAYNE BLVD GOING EAST . MORE INFORMATION CALL ME 561-703-1113 (TONY) &amp; ANTONIO.VALLADARES@SUNGUIDE.INFO THE DIRECT CONTACT : PAUL PIWAROMAS (954-895-7055) PAULP@TRAFFICMGMTSOLUTIONS.COM CHRIS SHAW (TMS SITE MANAGER) 786-423-3137 CSHAW@TRAFFICMGMTSOLUTIONS.COM.
| Current | MIAMI DADE COUNTY ISD FIMD UTILITIES SECTION | 4: Clear No Facilities
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/04/17 08:24 CONFLICT,REFER TO TKT # 105004817 MARKED FOR "NEW ERA ELECTRIC INC " 04/16.
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 4: Clear No Facilities
| Current | CENTURYLINK | 1: Marked
| Current | TRAFFIC MANAGEMENT SOLUTIONS | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 1: Marked