## OVERVIEW
CWSI - 1800 S University Rd (MIRAMAR) 700'
231 | 192000031
BLUE STREAK - 02A46091N (FT LAUDERDALE) SW 27th Ave
218 | 182004207
182005125
182005149
182005203
FTE Wellington High School
217 | 182003920
182003938
182003968
UNDERCITY - SW 87th Ave (WESTCHESTER / MIAMI)
215 | 169007575
HOTWIRE - TM 43 P534-535 (MIAMI) SW 11th St & S Miami Ave
214 | 167003972
167003985
195004787
195004795
HOTWIRE - TM-62 FOC (MIAMI) Brickell Ave
213 | 167004030
167004043
167004064
BLUE STREAK - 02A59083N (PARKLAND) PINE ISLAND
210 | 155007533
155007536
155007540
155007541
155007546
155007548
155007549
155007551
155007552
BLUE STREAK - 02A55028D (SUNRISE) NOB HILL RD & OAKLAND PARK BLVD
209 | 153005417
BLUE STREAK - 02A55034N (SUNRISE) NW 103RD AVE & NW 44TH ST
207 | 149002024
149002049
BLUE STREAK - 0EA46399N (DAVIE) SW 38TH CT & DAVIE RD
206 | 182006038
182006056
182006139
182006177
182006216
BLUE STREAK - 9EA31173N (PLANTATION) W BROWARD BLVD & S PINE ISLAND
205 | 148004700
148004722
148004739
148005174
161003905
BLUE STREAK - 09EA59150A (CORAL SPRINGS) ATLANTIC BLVD & RAMBLEWOOD DR
201 | 136005768
136005770
136005772
136005773
BLUE STREAK - 9EA55082D (SUNRISE) WALGREENS W OAKLAND PARK BLVD
176 | 135002070
BLUE STREAK - 02A25029N (FT LAUD) SE 3RD AVE
161 | 125003775
125003793
BLUE STREAK - 9EA02912N (WESTON) FALCON COVE MIDDLE SCHOOL
142 | 100006790
100006794
100006798
BLUE STREAK - 9EA02904N (WESTON) S POST RD
140 | 106002947
106002956
BLUE STREAK - 02A75070N (HOLLYWOOD) 1805 PIERCE ST CHURCH
137 | 096000203
096000207
BLUE STREAK - Permit# 2019-230-TL (PARKLAND) Fire Station 109 W HILLSBORO BLVD
129 | 090007341
090007344
090007345
090007347
090007348
BLUE STREAK - 02A25085N FT LAUD (SE 9TH ST)
116 | 076007085
076007087

## 231
CWSI - 1800 S University Rd (MIRAMAR) 700'
192000031
| Current | BROWARD COUNTY WATER AND WASTEWATER SERVICES | 4: Clear No Facilities
| Current | FDOT/ELAND ENGINEERING | 1: Marked
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | CITY OF MIRAMAR | 1: Marked
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CITY OF PEMBROKE PINES PUBLIC SERVICES | 3U: Unmarked - Not service provider for this location
| Current | HOTWIRE COMMUNICATIONS | 1: Marked
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA CITY GAS | 5: No Conflict - utility is outside of the requested work site
| Current | CENTURYLINK | 1: Marked

## 218
BLUE STREAK - 02A46091N (FT LAUDERDALE) SW 27th Ave
182004207
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | HEAVY CONSTRUCTION IN AREA. MARKS MAY BE AFFECTED.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | CROWN CASTLE NG | 1: Marked
182005125
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | HEAVY CONSTRUCTION IN AREA. MARKS MAY BE AFFECTED.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
182005149
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | HEAVY CONSTRUCTION IN AREA. MARKS MAY BE AFFECTED.
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | CROWN CASTLE NG | 1: Marked
182005203
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | HEAVY CONSTRUCTION IN AREA. MARKS MAY BE AFFECTED.
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked

## 217
FTE Wellington High School
182003920
| Current | WELLINGTON PALM BEACH COUNTY | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | COMCAST-PBG | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 1: Marked
182003938
| Current | WELLINGTON PALM BEACH COUNTY | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | COMCAST-PBG | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 1: Marked
182003968
| Current | WELLINGTON PALM BEACH COUNTY | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | FLORIDA POWER &amp; LIGHT - PALM BEACH | 1: Marked

## 215
UNDERCITY - SW 87th Ave (WESTCHESTER / MIAMI)
169007575
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | MCI | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 4: Clear No Facilities
| Current | FLORIDA GAS TRANSMISSION | 2C: Marked with Exceptions - High priority subsurface installation in conflict. Excavator MUST notify the member of the excavation or demolition start date and time. See s.556.116(1) and (2), F.S.
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 3P: Unmarked - Member does not have accurate information to perform the requested locate - please contact the utility for further details per 556.105 (7)(a), F.S.
| Current | FLORIDA CITY GAS | 1: Marked

## 214
HOTWIRE - TM 43 P534-535 (MIAMI) SW 11th St & S Miami Ave
167003972
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 1: Marked | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ABOVE GROUND RED AND WHITE PVC MARKERS (HIGH VOLTAGE). ANY QUESTIONS OR ASSISTANCE TO AVOID DAMAGE CALL STEVE AT (305) 797-8459. FPL TRANSMISSION IS LOCATED ON SW 1ST AVE ON THE WEST SIDE OF THE METRO RAIL, GOING NORTH AND SOUTH.
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/06/17 16:06 SPOKE WITH CESAR PHONE: 786-403-1546 CONTRACTOR WAS ADVISED OF DELAY TILL LOCATED APPROX BY FRIDAY 6/19 2020/06/19 17:26 SPOKE WITH CESAR PHONE: 786-403-1546 CONTRACTOR WAS ADVISED OF ADVISED OF DELAY TILL LOCATED APPROX BY MONDAY 6/22 2020/06/22 17:21 SPOKE WITH CESAR PHONE: 786-403-1546 CONTRACTOR WAS ADVISED OF DELAY TILL LOCATED APPROX BY FRIDAY 6/26 2020/07/06 18:08 SPOKE WITH CESAR 7864031546 CONTRACTOR WAS ADVISED OF DELAY TO LOCATED APPROXIMATELY BY FRIDAY 7/10 2020/07/10 17:41 SPOKE WITH JAMIE CONTRACTOR WAS ADVISED OF DELAY APPROXIMATELY TILL MONDAY 7/13
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
167003985
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--DADE | 1: Marked | 2020/07/10 17:40 SPOKE WITH JAMIE CONTRACTOR WAS ADVISED OF DELAY APPROXIMATELY TILL MONDAY 7/13 2020/07/11 12:41 PICTURES SEE TICKET#167003972
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
195004787
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 1: Marked | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS OR ASSISTANCE TO AVOID DAMAGE CALL STEVE (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM. FPL TRANSMISSION IS LOCATED ON THE WEST SIDE OF THE METRO RAIL ON SW 1ST AVE, GOING NORTH AND SOUTH.
| Current | MASTEC INC | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | MIAMI-DADE WATER &amp; SEWER | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--DADE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
195004795
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | FLORIDA DEPARTMENT OF TRANSPORTATION VI ITS | 4: Clear No Facilities
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | MCI | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 5: No Conflict - utility is outside of the requested work site
| Current | A T &amp; T/ DISTRIBUTION | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | COMCAST CABLE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | FLORIDA POWER &amp; LIGHT--DADE | 3F: Unmarked - Marking delay requested by locate technician and agreed to by excavator per agreement.
| Current | HOTWIRE COMMUNICATIONS | 6A: Active Facilities are present - the member has active facilities within the area described by the noticed demolition. DO NOT demolish until the member notifies you the site is clear
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 213
HOTWIRE - TM-62 FOC (MIAMI) Brickell Ave
167004030
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ABOVE GROUND RED AND WHITE PVC MARKERS (HIGH VOLTAGE). ANY QUESTIONS OR ASSISTANCE TO AVOID DAMAGE CALL STEVE AT (305) 797-8459. FPL TRANSMISSION IS LOCATED ON SE 6TH ST ON THE ROAD, GOING EAST AND WEST.
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CENTURYLINK | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
167004043
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS OR ASSISTANCE TO AVOID DAMAGE CALL STEVE (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM. FPL TRANSMISSION IS LOCATED ON THE ROAD ON SE 6TH ST, GOING EAST AND WEST.
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CENTURYLINK | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | MASTEC INC | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 3C: Unmarked - Locate technician and contractor (excavator) have agreed to meet on site on a specified date.
167004064
| Current | SSOCOF TEST CODE - DO NOT READ TO CALLER | 9Z: Call Center Test Destination - The member code affiliated with this code is a test code - please disregard this response
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--TRANSMISSION | 2A: Marked with Exceptions- High profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance | 138 KV FPL TRANSMISSION LINES PRESSURIZED AT 200 PSI. IN THE WORK AREA, DO NOT DRILL NEED TO MEET ON SITE BEFORE WORKING IN THIS AREA. ANY QUESTIONS OR ASSISTANCE TO AVOID DAMAGE CALL STEVE (305) 797-8459. OPERATION HRS. TO CALL, M-F 6AM TO 2:30 PM. FPL TRANSMISSION IS LOCATED ON THE ROAD ON SE 6TH ST, GOING EAST AND WEST.
| Current | FLORIDA POWER &amp; LIGHT - DOWNTOWN MIAMI | 2B: Marked with Exceptions - Privately owned Facilities on property, contact private facility owner directly. | THIS LOCATE HAS BEEN MARKED AS REQUESTED
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CENTURYLINK | 1: Marked
| Current | MIAMI-DADE WATER &amp; SEWER | 1: Marked
| Current | DADE COUNTY PUBLIC WORKS AND TRAFFIC | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | A T &amp; T/ DISTRIBUTION | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 5: No Conflict - utility is outside of the requested work site
| Current | MASTEC INC | 1: Marked

## 210
BLUE STREAK - 02A59083N (PARKLAND) PINE ISLAND
155007533
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007536
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007540
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007541
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
155007546
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007548
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007549
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007551
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
155007552
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 1: Marked
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | MCI | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked

## 209
BLUE STREAK - 02A55028D (SUNRISE) NOB HILL RD & OAKLAND PARK BLVD
153005417
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | CITY OF SUNRISE GAS | 2C: Marked with Exceptions - High priority subsurface installation in conflict. Excavator MUST notify the member of the excavation or demolition start date and time. See s.556.116(1) and (2), F.S.
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | CENTURYLINK | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked

## 207
BLUE STREAK - 02A55034N (SUNRISE) NW 103RD AVE & NW 44TH ST
149002024
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF SUNRISE GAS | 4: Clear No Facilities
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | CENTURYLINK | 1: Marked
149002049
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | CITY OF SUNRISE GAS | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CENTURYLINK | 1: Marked

## 206
BLUE STREAK - 0EA46399N (DAVIE) SW 38TH CT & DAVIE RD
182006038
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | FERNCREST UTILITIES | 4: Clear No Facilities
| Current | TOWN OF DAVIE - UTILITIES DEPARTMENT | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
182006056
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | FERNCREST UTILITIES | 4: Clear No Facilities
| Current | TOWN OF DAVIE - UTILITIES DEPARTMENT | 3H: Unmarked - Privately owned facilities on property, contact private facility owner directly.
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
182006139
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | FDOT/ELAND ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | TOWN OF DAVIE - UTILITIES DEPARTMENT | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 3D: Unmarked - High Profile utility in conflict, utility owner will attempt to contact you to schedule site surveillance
182006177
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | TOWN OF DAVIE - UTILITIES DEPARTMENT | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
182006216
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TOWN OF DAVIE - UTILITIES DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site

## 205
BLUE STREAK - 9EA31173N (PLANTATION) W BROWARD BLVD & S PINE ISLAND
148004700
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
148004722
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
148004739
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
148005174
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 4: Clear No Facilities
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
161003905
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF PLANTATION UTILITIES DEPARTMENT | 1: Marked
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/06/11 18:20 ADVISED CESAR LOCATE WILL BE COMPLETED BY , 06/15/20 4:00 PM

## 201
BLUE STREAK - 09EA59150A (CORAL SPRINGS) ATLANTIC BLVD & RAMBLEWOOD DR
136005768
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF CORAL SPRINGS | 4: Clear No Facilities
| Current | CORAL SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS DBA BLUE STREAM | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
136005770
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF CORAL SPRINGS | 1: Marked
| Current | CORAL SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS DBA BLUE STREAM | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/05/21 08:35 136005768
136005772
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF CORAL SPRINGS | 1: Marked
| Current | CORAL SPRINGS IMPROVEMENT DISTRICT | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | ADVANCED CABLE COMMUNICATIONS DBA BLUE STREAM | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/05/21 08:35 136005768
136005773
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF MARGATE | 3U: Unmarked - Not service provider for this location
| Current | DIRECT PLUS, LLC. | 4: Clear No Facilities
| Current | CITY OF CORAL SPRINGS | 1: Marked
| Current | CORAL SPRINGS IMPROVEMENT DISTRICT | 5: No Conflict - utility is outside of the requested work site
| Current | COMCAST CABLE | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS DBA BLUE STREAM | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/05/21 08:36 136005768
| Current | BROWARD COUNTY WATER AND WASTEWATER SERVICES | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | CITY OF NORTH LAUDERDALE | 3R: Unmarked - The excavator has performed the excavation prior to the locaters arrival

## 176
BLUE STREAK - 9EA55082D (SUNRISE) WALGREENS W OAKLAND PARK BLVD
135002070
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CITY OF LAUDERHILL | 3U: Unmarked - Not service provider for this location
| Current | AMERICAN TRAFFIC SOLUTIONS | 4: Clear No Facilities
| Current | MCI | 4: Clear No Facilities
| Current | CITY OF SUNRISE GAS | 1: Marked
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CITY OF SUNRISE WATER &amp; WASTEWATER DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site

## 161
BLUE STREAK - 02A25029N (FT LAUD) SE 3RD AVE
125003775
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
125003793
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site

## 142
BLUE STREAK - 9EA02912N (WESTON) FALCON COVE MIDDLE SCHOOL
100006790
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 4: Clear No Facilities
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-
100006794
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-
100006798
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | ELAND ENGINEERING / FDOT DISTRICT 4 | 4: Clear No Facilities
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON | 1: Marked
| Current | CITY OF PEMBROKE PINES / CH2M | 3U: Unmarked - Not service provider for this location
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/13 18:07 DEAR 811 LOCATE RECIPIENT, USIC LOCATING SERVICES 3337 NW 55TH STREET FORT LAUDERDALE, FL 33309 811 CALL BEFORE YOU DIG THIS EMAIL IS TO DELAY THE LOCATE TICKET #100006790/100006794/100006798. THIS IS CONSIDERED A POSITIVE RESPONSE EMAIL ACKNOWLEDGING THE LOCATE TICKET REQUESTED ABOVE TO BE DELAYED DUE TO IN-FIELD SCHEDULING. IF YOU ARE GOING TO BE ONSITE WITHIN THE NEXT 12-24 HOURS REPLY ALL TO THE EMAIL AND/OR CALL THE NUMBER BELOW. IF THERE IS A HOLIDAY THEN PLEASE ADD A BUSINESS DAY. COMPLETING THE LOCATE TICKET ON TIME AND MARKING IT CORRECTLY IS OUR TOP PRIORITY AND WE WANT TO ENSURE THAT YOU ARE SATISFIED WITH OUR WORK. IF THERE ARE ANY ISSUES THAT ARISE IN BETWEEN THE TIME YOU HAVE READ THIS EMAIL TO THE TIME YOUR LOCATE TICKET IS COMPLETED PLEASE CALL THE USIC DISPATCH LINE @ 317-575-7800 AND PRESS OPT 1. PLEASE NOTE THAT THIS IS THE POSITIVE RESPONSE DELAYING THE LOCATE TICKET. SINCERELY, GEORGE RODRIGUEZ 954-240-4009 USIC LOCATING SERVICES-

## 140
BLUE STREAK - 9EA02904N (WESTON) S POST RD
106002947
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | ADVANCED CABLE COMMUNICATIONS | 1: Marked
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/16 09:47 FACILITIES MARKED FOLLOW FLAGS AND PAINT, REFER TO PICS. BE ADVISED NO DETAILED PRINTS FOR ADVANCED CABLE, VERIFIED ON SITE. 106002947
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked
106002956
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MASTEC INC | 4: Clear No Facilities
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | ADVANCED CABLE COMMUNICATIONS | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/16 09:48 FACILITIES MARKED FOLLOW FLAGS AND PAINT, REFER TO PICS. BE ADVISED NO DETAILED PRINTS FOR ADVANCED CABLE, VERIFIED ON SITE. 106002947
| Current | CITY OF WESTON- ELECTRIC | 1: Marked
| Current | CITY OF WESTON- IRRIGATION | 1: Marked
| Current | CITY OF WESTON- DRAINAGE | 1: Marked
| Current | CITY OF WESTON - FIBER OPTIC | 5: No Conflict - utility is outside of the requested work site
| Current | CITY OF WESTON | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 1: Marked

## 137
BLUE STREAK - 02A75070N (HOLLYWOOD) 1805 PIERCE ST CHURCH
096000203
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | MCI | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | WINDSTREAM COMMUNICATION | 1: Marked
| Current | CITY OF HOLLYWOOD PUBLIC UTILITIES DEPT | 1: Marked | GPR-R LOCATING USED.
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 1: Marked
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
096000207
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | MASTEC INC | 4: Clear No Facilities
| Current | ATLANTIC BROADBAND | 1: Marked
| Current | CROWN CASTLE NG | 1: Marked
| Current | MCI | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 4: Clear No Facilities
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 1: Marked
| Current | CITY OF HOLLYWOOD PUBLIC UTILITIES DEPT | 1: Marked | GPR-R LOCATING USED.
| Current | CITY OF HOLLYWOOD, PUBLIC WORKS DEPARTMENT | 1: Marked | OFFSETS USED IN LOCATE.
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 2E: Marked with Exceptions - Marked within the confines of white-lined area

## 129
BLUE STREAK - Permit# 2019-230-TL (PARKLAND) Fire Station 109 W HILLSBORO BLVD
090007341
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 2E: Marked with Exceptions - Marked within the confines of white-lined area
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked | 2020/04/01 14:42 TALKED TO MIKE THEY STARTED TODAY I WILL DO FIRST THING TOMORROW
090007344
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007345
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007347
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
090007348
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | HOTWIRE COMMUNICATIONS | 4: Clear No Facilities
| Current | NORTH SPRINGS IMPROVEMENT DISTRICT | 1: Marked
| Current | PALM BEACH COUNTY WATER UTILITIES | 4: Clear No Facilities
| Current | COMCAST CABLE | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked

## 116
BLUE STREAK - 02A25085N FT LAUD (SE 9TH ST)
076007085
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | CENTURYLINK | 5: No Conflict - utility is outside of the requested work site
| Current | WINDSTREAM COMMUNICATION | 4: Clear No Facilities
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | BROWARD COUNTY TRAFFIC ENGINEERING | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | CITY OF FT LAUDERDALE | 1: Marked
076007087
| No Response, Current | A T &amp; T/ DISTRIBUTION
| Current | FLORIDA POWER &amp; LIGHT - SUBAQUEOUS | 5: No Conflict - utility is outside of the requested work site
| Current | TECO PEOPLES GAS SOUTH FLORIDA | 5: No Conflict - utility is outside of the requested work site
| Current | CROWN CASTLE NG | 4: Clear No Facilities
| Current | COMCAST CABLE | 1: Marked
| Current | FLORIDA POWER &amp; LIGHT--BROWARD | 1: Marked
| Current | WINDSTREAM COMMUNICATION | 1: Marked
| Current | CITY OF FT LAUDERDALE | 1: Marked
| Current | AT T | 5: No Conflict - utility is outside of the requested work site | NULL
| Current | CENTURYLINK | 1: Marked